## Slide 1: MS Project course
Danny Puype - 2024

## Slide 2
Structure
Demo
1. Planning
3. Reporting
Todo’s - WBS
Resources
Links
Info …
2. Tracking
Realiteit inbrengen
Auto update
Planning aanpassen
4. Multi-projects

## Slide 3
Environ-ment
Weergaves
Omgeving
Zoom
Taken
Tabellen
Contextuele linten
WBS
Tijdsschaal
Overzichtstaken
Subtaken
Constraints - beperkingen
ASAP
Auto / manual
3 Dimensies
Planning
Baseline
Actual
Opties
QAT
Rekenopties: in minuten
Scherm splitsen
Linten
Kalenders

## Slide 4: Nieuw project
Configuratie
Start datum
Omschrijving, doel, metadata
WBS – structuren
  Weerkerende taken
  Subtaken
  Mijlpalen
Deadlines en beperkingen

## Slide 5: Links
Linken
Voorafgaande en opvolgende taken
Buffer
Linken tussen subtaken of overzichtstaken
FS / BE
SS / GB
FF / GE
SF / EB
Methodes
snelkoppeling
form
velden
Simuleren

## Slide 6: Opmaak
Tekst
Balken
Vrije tekst
Stijlen
Gantt stijlen
Balk stijlen
Balken apart
Lijnen
Layout Indeling
Extra
Context linten

## Slide 7: Resources
Input
Toekenning
Finetuning
Overbezetting
? Waarom
Werk = Duur * Capaciteit
Formule
Type taak
Effort driven

## Slide 8
Task type | Work Travail | Duration Durée | Units Capacité
Fixed Work Travail Fixe | Duration Durée | Peak Pointe | Duration Durée
Fixed Duration Durée Fixe | Peak Pointe | Work Travail | Work Travail
Fixed Units Capacité Fixe | Duration Durée | Work Travail | Duration Durée

## Slide 9
14 nov '22
21 nov '22
28 nov '22
05 dec '22
12 dec '22
19 dec '22
26 dec '22
02 jan '23
09 jan '23
Uitgravingen sleuven 02-12-22 - 22-12-22
Grondverzet 29-11-22 - 15-12-22
Aanvullingen 22-12-22 - 11-01-23
✔Uitgravingen van de bouwputten 07-11-22 - 30-11-22
✔Uitgravingen zijn uitgevoerd 30-11-22
Grondwerken zijn af 12-01-23

## Slide 10: Tracking - Opvolging
Baseline = roadmap = ideale planning
= ‘Actuals’ invullen = werkelijkheid
  Start – Einde - Duurtijd
  Werkelijk werk
  Werkelijke kosten
Hoe
  %
  Bijwerken taak
  Formulier Werk
  Andere weergaves
Planning voortdurend herberekend
  Evalueren
  ? Update ‘on track’

## Slide 11: Rapportering
Printen
Tijdslijn
Export
Excel
Word/PWP
Rapporten
Filters / Groeperen

## Slide 12: 10 insights to ‘crack’ MS Project

## Slide 13: 1. MS Project is a database
All views and tables show the same data from different perspectives.
The database is built upon 3 axes of main tables:
  Tasks
  Resources
  Assignments
There are tons of fields to customize – get to know them

## Slide 14: 2. MS Project is a calculator
Everything is recalculated to minutes. And then shown in time-units asper your configuration settings.
In the Options you determine the algorithms to be used in the calendars.

## Slide 15: 3. Start each project schedule by checking your basic configuration settings
These include your default calendar, the calendar calculations, metadata, currency and time settings.
Use templates to save all settings

## Slide 16: 4. Let MS Project calculate for you
Let it calculate start and end times for you! Don’t enter dates by default.
The schedule adapts on the basis of the dependencies you’ve set, the durations, task configurations and resource settings.

## Slide 17: 5. MS Project is programmed to be asap
Don't put constraints initially; if needed put them in when project is ongoing and consider carefully. Beware that changing dates is going to trigger off constraints other than asap or alap.
Use manual tasks if you want to enter dates for tasks and control manually.

## Slide 18: 6. Use an outline code to discern your task levels and WBS structure
You can use the default one or your own.
Add outline zoom, timescale zoom and other navigation button to the QAT

## Slide 19: 7. Each of the 3 main (input) fields have three manifestations / versions.
Input happens in duration | work | cost fields
To be able to manage a project you need 3 versions of those fields :
  scheduled
  baseline
  actual
The different versions are shown in different views and tables.

## Slide 20: 8. Set the timescales to weeks and month for easier management.
The default setting is by days and weeks in most views.
Zooming out the time scale to weeks and months is in many cases a key to handle the project more smoothly; e.g. assessing over-allocation or using time-scaled views.

## Slide 21: 9. Think in work-terms as much as possible.
Use different time measurements for durations and work. If you prefer to express work in man-days, do so, but then express duration in weeks.
When resources are assigned, a formula (W = D * U ) is triggered off to calculate work. Each change in one of the parameters of this equation is going to trigger off recalculations in function of
  1) the type of the task (Fixed U, D, W) and
  2) whether the task is effort driven or not.

## Slide 22: 10. Tracking a project = entering actuals
To track values, search for the appropriate ‘actual’ field and enter the data.

## Slide 23: Resources
MS Project resources
  https://www.youtube.com/watch?v=OuOZVoTwqm8&list=PLe2KBvAeoZPczYIFNd-ZhvHQVwUYJPJKn&index=7&t=2345s : Beginner course
  https://www.youtube.com/watch?v=1vzGD6igNSA&list=PLe2KBvAeoZPczYIFNd-ZhvHQVwUYJPJKn&index=10&t=10s : Advanced course
  http://cnaiman.com/PM/MIT-LabText/2016/MP.2016.Step.by.Step.pdf : Step by Step manual
  https://boyleprojectconsulting.com/tomsblog/browsetitles/using-microsoft-project-msp/ : Tom’s Blog
  Jack Dahlgren’s code & publications: https://www.stakeholdermap.com/ms-project/ms-project-vba.html
  Format Duration macro: https://www.project-systems.co.nz/project-vba-macros/FormatDuration.html
Alternatives
  https://clickup.com/blog/microsoft-project-alternatives/
  https://www.projectlibre.com
  https://monday.com/blog/project-management/the-complete-project-management-software-list/